## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
13 | User Login | Ryan | 1 | 3 | Included in Sprint 1 | The business mission is displayed somewhere on the page Contact Details are displayed somewhere on the page Implemented a button to redirect to login page Tested with Postman
12 | Home page about/contact us section | Hollie | 2 | 2 | Included in Sprint 1 | The business mission is displayed somewhere on the page Contact Details are displayed somewhere on the page Implemented a button to redirect to login page Tested with Postman
1 | Customer Registration | Matthies | 3 | 4 | Included in Sprint 1 | Logout button visible on all pages once any type of user is logged in. Back end processes logout button click appropriately Redirection to index page User is not logged in anymore and cannot go back on browser history to 're-login'. Tested with Postman
2 | Logout | Ryan | 4 | 1 | Included in Sprint 1 | Logout button visible on all pages once any type of user is logged in. Back end processes logout button click appropriately Redirection to index page User is not logged in anymore and cannot go back on browser history to 're-login'. Tested with Postman
4 | Customer view services | Matthies | 5 | 3 | Included in Sprint 1 | Services are listed on the dashboard with a business name and logo in a formatted matter. Back end processes metadata of all services to be displayed on dashboard. Redirection to the appropriate service page when clicked. Tested with Postman
21 | Customer makes booking | Jordan | 6 | 3 | Included in Sprint 1 | The customer details form is displayed with all relevant credentials needed to place a booking. Back end processes accepts / rejects form input appropriately When inappropriate input is given user is shown how to correct mistakes Redirection to booking confirmation Tested with Postman
5 | Customer view available time slots |  | 7 | 4 | On Product Backlog
11 | Customer views worker on time slot |  | 8 | 2 | On Product Backlog
21 | Customer views upcoming bookings |  | 9 | 3 | On Product Backlog
19 | Administrator views current bookings |  | 10 | 2 | On Product Backlog
10 | Worker views assigned bookings |  | 11 | 2 | On Product Backlog
9 | Customer cancels a booking |  | 12 | 2 | On Product Backlog
3 | Customer edits bookings |  | 13 | 3 | On Product Backlog
16 | Administrator edits business hours times/dates |  | 14 | 3 | On Product Backlog
8 | Administrator edits bookings |  | 15 | 3 | On Product Backlog
17 | Customer update information |  | 16 | 2 | On Product Backlog
14 | Administrator adds employees |  | 17 | 2 | On Product Backlog
20 | Administrator views booking contact details |  | 18 | 2 | On Product Backlog
18 | Automatically notify customer of changes to booking |  | 19 | 3 | On Product Backlog
15 | Administrator view past bookings |  | 20 | 2 | On Product Backlog
7 | User change password |  | 21 | 1 | On Product Backlog
6 | Password recovery |  | 22 | 4 | On Product Backlog
27
28
29
30
31
32
33
34
35
36
37
38
39
40
On Product Backlog

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | User Login | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Home page about/contact us section | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Customer Registration | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Logout | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Customer view services | #N/A | #N/A | #N/A | #N/A | #N/A
6 | Customer makes booking | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Customer view available time slots | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Customer views worker on time slot | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Customer views upcoming bookings | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Administrator views current bookings | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Worker views assigned bookings | #N/A | #N/A | #N/A | #N/A | #N/A
12 | Customer cancels a booking | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Customer edits bookings | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Administrator edits business hours times/dates | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Administrator edits bookings | #N/A | #N/A | #N/A | #N/A | #N/A
16 | Customer update information | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Administrator adds employees | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Administrator views booking contact details | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Automatically notify customer of changes to booking | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Administrator view past bookings | #N/A | #N/A | #N/A | #N/A | #N/A
21 | User change password | #N/A | #N/A | #N/A | #N/A | #N/A
22 | Password recovery | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A