## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
13 | User Login | Ryan | 1 | 3 | Complete in sprint 3 | The business mission is displayed somewhere on the page Contact Details are displayed somewhere on the page Implemented a button to redirect to login page Tested with Postman
12 | Home page about/contact us section | Hollie | 2 | 2 | Complete in sprint 2 | The business mission is displayed somewhere on the page Contact Details are displayed somewhere on the page Implemented a button to redirect to login page Tested with Postman
1 | Customer Registration | Matthies | 3 | 4 | Complete in sprint 2 | Logout button visible on all pages once any type of user is logged in. Back end processes logout button click appropriately Redirection to index page User is not logged in anymore and cannot go back on browser history to 're-login'. Tested with Postman
2 | Logout | Ryan | 4 | 1 | Complete in sprint 3 | Logout button visible on all pages once any type of user is logged in. Back end processes logout button click appropriately Redirection to index page User is not logged in anymore and cannot go back on browser history to 're-login'. Tested with Postman
4 | Customer view services | Matthies | 5 | 3 | Complete in sprint 2 | Services are listed on the dashboard with a business name and logo in a formatted matter. Back end processes metadata of all services to be displayed on dashboard. Redirection to the appropriate service page when clicked. Tested with Postman
5 | Customer view available time slots |  | 6 | 9 | Complete in sprint 2
21 | Customer makes booking | Jordan | 7 | 3 | Complete in sprint 3 | The customer details form is displayed with all relevant credentials needed to place a booking. Back end processes accepts / rejects form input appropriately When inappropriate input is given user is shown how to correct mistakes Redirection to booking confirmation Tested with Postman
11 | Customer views worker on time slot |  | 8 | 4 | Included in Sprint 3 | Readjust 'Timeslot' data to have a parameter for 'WokerAssigned' Readjust GET request from timeslots to also grab and display the worker assigned on the front end Display worker name on the front end for each timeslot Tested
22 | Customer views upcoming bookings |  | 9 | 6 | Complete in sprint 3 | Create a Backend function for collating all upcoming booking for a given customer Create GET request for all upcoming booking of a given customer Rework user profile page to have a section for customers to view their upcoming bookings Tested
19 | Administrator views current bookings |  | 12 | 7 | On Product Backlog
10 | Worker views assigned timeslots |  | 14 | 8 | On Product Backlog
9 | Customer cancels a booking |  | 15 | 4 | On Product Backlog
3 | Customer edits bookings |  | 17 | 3 | On Product Backlog
16 | Administrator edits business hours times/dates |  | 11 | 3 | On Product Backlog
8 | Administrator edits bookings |  | 23 | 3 | On Product Backlog
17 | Customer update information |  | 16 | 2 | On Product Backlog
14 | Administrator adds employees |  | 13 | 2 | On Product Backlog
20 | Administrator views booking contact details |  | 18 | 2 | On Product Backlog
18 | Automatically notify customer of changes to booking |  | 19 | 3 | On Product Backlog
15 | Administrator view past bookings |  | 20 | 2 | On Product Backlog
7 | User change password |  | 21 | 1 | On Product Backlog
6 | Password recovery |  | 22 | 4 | On Product Backlog
23 | Types of Accounts |  | 10 | 4 | Completed in Sprint 3 | Back end 'Account' data type readjusted to have a parameter for types of accounts Login redirection is based on the type of account returned from the GET request Tokenization Tested
On Product Backlog

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | User Login | #N/A | #N/A | #N/A | #N/A | #N/A
2 | Home page about/contact us section | #N/A | #N/A | #N/A | #N/A | #N/A
3 | Customer Registration | #N/A | #N/A | #N/A | #N/A | #N/A
4 | Logout | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Customer view services | #N/A | #N/A | #N/A | #N/A | #N/A
6 | Customer view available time slots | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Customer makes booking | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Customer views worker on time slot | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Customer views upcoming bookings | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Administrator views current bookings | #N/A | #N/A | #N/A | #N/A | #N/A
11 | Worker views assigned timeslots | #N/A | #N/A | #N/A | #N/A | #N/A
12 | Customer cancels a booking | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Customer edits bookings | #N/A | #N/A | #N/A | #N/A | #N/A
14 | Administrator edits business hours times/dates | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Administrator edits bookings | #N/A | #N/A | #N/A | #N/A | #N/A
16 | Customer update information | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Administrator adds employees | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Administrator views booking contact details | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Automatically notify customer of changes to booking | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Administrator view past bookings | #N/A | #N/A | #N/A | #N/A | #N/A
21 | User change password | #N/A | #N/A | #N/A | #N/A | #N/A
22 | Password recovery | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Types of Accounts | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A