## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES (ESTIMATE. TIME SPENT)
13 | User Login | 13.1 | Create Login Form | Hollie |  |  | X | Estimate hours: 2, Actual hours: 2
|  | 13.2 | Validate user/password against database | Ryan |  | X |  | Estimate hours: 2, Actual hours: 1
|  | 13.3 | Validation messages | Ryan |  |  | X | Estimate hours: 1, Actual hours: 0
|  | 13.4 | Login framework code | Ryan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 13.5 | User Login Redirect | Hollie |  | X |  | Estimate hours: 2, Actual hours: 1
|  | 13.6 | Login Validation | Hollie | X |  |  | Estimate hours: 3, Actual hours: 0
|  | 13.7 | Testing | Luke |  | X |  | Estimate hours: 2, Actual hours: 0
1 | Customer Registration | 1.1 | Create Registration Form Component | Matthies |  |  | X | Estimate hours: 3, Actual hours: 3
|  | 1.2 | Redirection to Customer Dashboard | Matthies |  |  | X | Estimate hours: 2, Actual hours: 1
|  | 1.3 | Registration framework code | Ryan |  |  | X | Estimate hours: 2, Actual hours: 2
|  | 1.4 | Registration details validation | Ryan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 1.5 | Save registered user to database | Ryan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 1.6 | Invalid registration messages | Ryan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 1.7 | Duplicate user validation | Ryan |  |  | X | Estimate hours: 2, Actual hours: 2
|  | 1.8 | GET request registration input validation | Matthies | X |  |  | Estimate hours: 4, Actual hours: 0
|  | 1.9 | POST request for new user in database | Matthies | X |  |  | Estimate hours: 2, Actual hours: 0
|  | 1.10 | Testing | Luke |  | X |  | Estimate hours: 2, Actual hours: 1
4 | Customer View Services | 4.1 | Create Service Card Component | Matthies |  |  | X | Estimate hours: 4, Actual hours: 3
|  | 4.2 | POST request for creating a service | Jordan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 4.3 | GET requests for retrieving services | Jordan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 4.4 | Testing | Luke |  | X |  | Estimate hours: 2, Actual hours: 4
|  | 4.5 | GET request services for database | Matthies | X |  |  | Estimate hours: 4, Actual hours: 0
12 | Home page about/contact us section | 12.1 | Creating About Us Section | Hollie |  | X |  | Estimate hours: 2, Actual hours: 2
|  | 12.2 | Creating Contact Us Section | Hollie |  | X |  | Estimate hours: 1, Actual hours: 0
|  | 12.3 | Testing | Luke | X |  |  | Estimate hours: 1, Actual hours: 0
2 | Logout | 2.1 | Logout Redirection | Hollie | X |  |  | Estimate hours: 1, Actual hours: 0
|  | 2.2 | Logout of Session | Hollie | X |  |  | Estimate hours: 1, Actual hours: 0
|  | 2.3 | Testing | Luke | X |  |  | Estimate hours: 2, Actual hours: 0
21 |  | 21.1 | Testing | Luke | X |  |  | Estimate hours: 2, Actual hours: 0
|  | 21.2 | POST request for creating timeslot | Jordan |  | X |  | Estimate hours: 1, Actual hours: 2
|  | 21.3 | POST request for creating booking | Jordan | X |  |  | Estimate hours: 1, Actual hours: 0

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | User Login | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Customer Registration | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Customer View Services | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!