## Product Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | Customer registration | 1.1
1.2
1.3
1.4
1.5
1.6
1.7
|  | 1.8 | POST request for registration input validation | Matthies Abera |  |  | X | Estimate hours: 4, Actual hours: 4
|  | 1.9 | POST request new used in database | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 2
|  | 1.10 | Testing | Luke |  |  | X | Estimate hours: 2, Actual hours: 2
2 | Logout | 2.1 | Logout Redirection | Hollie |  | X
|  | 2.2 | Logout of Session | Hollie |  | X
|  | 2.3 | Design logout system | Ryan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 2.4 | Add logged in user tracking | Ryan |  | X |  | Estimate hours: 1, Actual hours: 2
|  | 2.5 | Add logout function | Ryan | X |  |  | Estimate hours: 2, Actual hours: 2
|  | 2.6 | Testing | Luke | X |  |  | Estimate hours: 2, Actual hours: 0
4 | Customer view services | 4.1
4.2
4.3
|  | 4.4 | Testing | Luke |  |  | X | Estimate hours: 2, Actual hours: 4
|  | 4.5 | GET request services for database | Matthies Abera |  |  | X | Estimate hours: 4, Actual hours: 4
5 | Customer views available time slots | 5.1 | Create Available Times Component View | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 1
|  | 5.2 | Create an Individual Time Component | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 1
|  | 5.3 | POST request for creating timeslot | Jordan |  |  | X | Estimate hours: 1, Actual hours: 3
|  | 5.4 | GET requests for retrieving timeslots | Jordan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 5.5 | Request to delete timeslot | Jordan
|  | 5.6 | GET request all available times from backend | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 4
|  | 5.7 | Show status of availability
|  | 5.8 | Testing | Luke |  |  | X | Estimate hours: 2, Actual hours: 3
12 | Home page about/contact us section | 12.1 | Creating About Us Section | Hollie |  |  | X
|  | 12.2 | Creating Contact Us Section | Hollie |  |  | X
13 | User Login | 13.1
13.2
13.3
13.4
|  | 13.5 | User Login Redirection | Hollie |  | X
|  | 13.6 | Login Validation | Hollie |  | X
|  | 13.7 | Testing | Luke |  |  | X | Estimate hours: 2, Actual hours: 1
21 | Customer makes booking | 21.1 | Testing | Luke | X |  |  | Estimate hours: 2, Actual hours: 1
21.2
|  | 21.3 | POST request for creating booking | Jordan |  |  | X | Estimate hours: 1, Actual hours: 2
|  | 21.4 | GET request for obtaining timeslot from booking id | Jordan |  |  | X | Estimate hours: 1, Actual hours: 1
|  | 21.5 | DELETE request for removing booking | Jordan |  |  | X | Estimate hours: 1, Actual hours: 1

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Customer registration | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | Logout | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Customer view services | #N/A | #N/A | #N/A | #N/A | #N/A
20 |  | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Customer views available time slots | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A