## Product Backlog
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
2 | Logout | 2.1 | Logout Redirection | Hollie |  |  | X | Estimated hours: 1, Actual hours: 1
|  | 2.2 | Logout of Session | Hollie |  |  | X | Estimated hours; 1, Actual hours: 1
2.3
|  | 2.4 | Add logged in user tracking | Ryan |  |  | X | Estimated hours: 2, Actual hours: 5
|  | 2.5 | Testing | Luke |  | X |  | Estimated hours: 1, Actual hours: 0.5
11 | Customer views worker on time slot | 11.1 | Re-adjust 'Timeslot' data to have a parameter for 'WokerAssigned' | Jordan |  |  | X | Estimated hours; 1, Actual hours: 1
|  | 11.2 | Readjust GET request from timeslots to also grab and display the worker assigned on the front end | Matthies | X |  |  | Estimated hours: 1, Actual hours: 0
|  | 11.3 | Display worker name on the front end for each timeslot | Matthies | X |  |  | Estimated hours: 1, Actual hours: 0
|  | 11.4 | Testing | Luke |  |  |  | Estimated hours: 1, Actual hours: 0
13 | User Login
|  | 13.5 | User Login Redirection | Hollie |  |  | X | Estimated hours: 2, Actual hours: 1
|  | 13.6 | Login Validation | Hollie |  |  | X | Estimated hours: 3, Actual hours: 2
21 | Customer makes booking | 21.1 | Testing | Luke |  |  | X | Estimated hours: 2, Actual hours: 1
|  | 21.6 | Book a timeslot in frontend | Hollie |  |  | X | Estimated hours: 1, Actual hours: 1
|  | 21.7 | Update timelot display | Hollie |  |  | X | Estimated hours; 1, Actual hours: 1
22 | Customer views upcoming bookings | 22.1 | Create a Backend function for collating all upcoming booking for a given customer | Jordan |  |  | X | Estimated hours: 1, Actual hours: 1
|  | 22.2 | Create GET request for all upcoming bookings of a given customer | Matthies |  |  | X | Estimated hours: 2, Actual hours: 1
|  | 22.3 | Rework user profile page to have a section for cutstomers to view their upcoming bookings | Matthies |  |  | X | Estimated hours: 3, Actual hours: 1
|  | 22.4 | Testing | Luke |  |  | X | Estimated hours: 1, Actual hours: 1
|  | 22.5 | Add price as field to timeslot | Jordan |  |  | X | Estimated hours; 1, Actual hours: 1
23 | Types of Accounts | 23.1 | Back end 'Account' data type re-adjusted to have functionality for different types of accounts | Jordan |  |  | X | Estimated hours: 1, Actual hours: 3
|  | 23.2 | Login redirection is based on the type of account returned from the GET request | Hollie |  |  | X | Estimated hours: 2, Actual hours: 1
|  | 23.3 | Testing | Luke |  |  | X
|  | 23.4 | Create connection between admin and workers in backend | Jordan |  |  | X | Estimated hours; 2, Actual hours: 1

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #REF!
| Previous Year | #REF! | #REF!
| Position | #REF! | #REF! | #REF! | #REF! | #REF!
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | Logout | #N/A | #N/A | #N/A | #N/A | #N/A
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  | #N/A | #N/A | #N/A | #N/A | #N/A
7 |  | #N/A | #N/A | #N/A | #N/A | #N/A
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Customer views worker on time slot | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 |  | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 | User Login | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 |  | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 |  | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Customer makes booking | #N/A | #N/A | #N/A | #N/A | #N/A
21 |  | #N/A | #N/A | #N/A | #N/A | #N/A
22 |  | #N/A | #N/A | #N/A | #N/A | #N/A
23 |  | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A